## 3. Function List
No | [9 empty] | Effort (manday) |  |  |  | Pricing by position |  |  |  |  | 13 | 8 | 5 | 3 | 2 | 1
|  | Task | Detial | r | sprint | Complexity | Screen | Process | Report | SM | SA | PG | Tester | SM | SA | PG | Tester 6,000 |  | 20 | 18 | 12 | 8 | 5 | 3
[10 empty] | 5% | 35% | 40% | 20% | 18000 | 12150 | 9700 | 7150
1 | New Car Insurance | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | New Car Insurance Activation List | 3_1_1 Show all vehicle data that received API from ddms- Select to detail for activated- Able to export raw data from list | 1 | 1 | 3 | 1 |  |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 |  | 0 | 0 | 0 | 8 | 0 | 0
| 1.2 | New Car Insurance Activation Detail | 3_1_2,3 Show detail each vehicle following selected from list screen- Click for activated- Click for deactivated (If any) | 1 | 1 | 13 | 1 | 1 |  | 2 | 14 | 16 | 8 | 36000 | 170100 | 155200 | 57200 |  | 40 | 0 | 0 | 0 | 0 | 0
| 1.3 | New Car Insurance Activation Report | 3_2: For download raw data from new car insurance | 1 | 2 | 5 |  |  | 1 | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 |  | 0 | 0 | 12 | 0 | 0 | 0
| 1.4 | INS Company Import - 1st year INS Sales Premium | 5_1 | 1 | 1 | 2 |  |  | 1 | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 |  | 0 | 0 | 0 | 0 | 5 | 0
| 1.5 | INS Company Export - 1st year INS Sales Daily | 5_1 | 1 | 2 | 2 |  |  | 1 | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 |  | 0 | 0 | 0 | 0 | 5 | 0
| 1.6 | New Car Insurance Edit |  | 1 | 2 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 |  | 0 | 18 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3 | Management | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 3.1 | 1st Time Data Allocation | 6_2_1_1 1st time data allocation | 1 | 2 | 13 | 1 |  |  | 1 | 7 | 8 | 4 | 18000 | 85050 | 77600 | 28600 |  | 20 | 0 | 0 | 0 | 0 | 0
| 3.2 | Insurance Premium Management | 6_4 INS Premium Mgmt Screen | 4 | 4 | 5 | 1 |  | 2 | 1.8 | 12.6 | 14.4 | 7.2 | 32400 | 153090 | 139680 | 51480 |  | 0 | 0 | 36 | 0 | 0 | 0
| 3.3 | New Car - Insurance Portfolio Management | 6_1_2_1 INS Activation Function | 4 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 |  | 0 | 18 | 0 | 0 | 0 | 0
| 3.4 | New Car - Insurance Activation Management | 6_1_2_1 INS Activation Function | 4 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 |  | 0 | 18 | 0 | 0 | 0 | 0
| 3.5 | New Car - Insurance Portfolio Management | 6_1_1_1 For manage portfolion that will impact to call plan, 2-3 New Car INS Portfolio MGMT | 3 | 4 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 |  | 0 | 0 | 12 | 0 | 0 | 0
| 3.6 | 1st Year(Red Plate) INS report | 6_5_1 | 2 | 4 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 |  | 0 | 0 | 12 | 0 | 0 | 0
| 3.7 | Customer Management - INS Premium Mgmt Screen | 6_3_1 INS Databased MGMT, 6_3_1 | 6 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 |  | 0 | 18 | 0 | 0 | 0 | 0
| 3.8 | Employee master - list | 6_3_2_1 Manpower and ACC Setting | 6 | 5 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 3.9 | Employee master - Detail | 6_3_2_2 Account by Acc Mgmt | 6 | 5 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 |  | 0 | 0 | 0 | 0 | 5 | 0
| 3.10 | Customer master - list |  | 6 | 5 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 3.11 | Customer master - Detail | 6_3_2_3 Inc Cust Ac Create | 6 | 5 | 3 | 1 |  |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 |  | 0 | 0 | 0 | 8 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
4 | Interface | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 4.1 | REST API insurance data to BP Accident App |  |  | 5 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 |  | 0 | 0 | 0 | 8 | 0 | 0
| 4.2 | REST API received vehicle data from DDMS |  |  | 5 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 |  | 0 | 0 | 0 | 8 | 0 | 0
| 4.3 | REST API received customer data from TOPSERV |  |  | 5 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 |  | 0 | 0 | 0 | 8 | 0 | 0
| 4.4 | REST API Send policy data to TOPSERV |  |  | 5 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 |  | 0 | 0 | 0 | 8 | 0 | 0
| 4.5 | REST API - SC API - Add | New,Update,delete user, user authorize |  | 5 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 4.6 | REST API - SC API - Update |  |  | 5 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 4.7 | REST API - SC API - Delete |  |  | 5 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 4.8 | REST API - SC API - user authorization |  |  | 6 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5 | Master | [8 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 5.1 | User ( Update/ Delete) | User role assigment |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 5.2 | User Group (Update/ Delete) | Role management | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 5.3 | Organization (Add/ Update/ Delete) | Organization of dealer |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 5.4 | Car Company (Toyota/Honda) |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 5.5 | Car Model (Yaris/ corolla) |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 5.6 | Province |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 5.7 | Amphur |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 5.8 | Tumbon |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 5.9 | Dealer | group dealer |  | 6 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 |  | 0 | 0 | 0 | 0 | 5 | 0
| 5.10 | Insurance |  |  | 6 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 |  | 0 | 0 | 0 | 0 | 5 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6 | Data Migration | [8 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 6.1 | User ( Update/ Delete) | sales |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 6.2 | User Group (Update/ Delete) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 6.3 | Organization (Add/ Update/ Delete) | sales organize |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 6.4 | Customer Vehicel |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 6.5 | Customer |  |  | 6 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 |  | 0 | 0 | 0 | 0 | 5 | 0
| 6.6 | Vehicle Insurance mapping |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 6.7 | Dealer |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
| 6.8 | Insurance |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 |  | 0 | 0 | 0 | 0 | 0 | 3
|  | Total |  |  |  |  | 30 | 9 | 5 | 16.95 | 118.65 | 135.6 | 67.8 | 305100 | 1441597.5 | 1315320 | 484770
3546787.5
[11 empty] | 339 | 10.17
16.95
5.9325
[5 empty] | SM | SA | SPG | Tester | MD | MM | Screen | Batch | Report | SM MP | SA MP | SPG MP | Tester MP
|  | Sprint | 1 |  | 2.65 | 18.55 | 21.2 | 10.6 |  | 53 | 2.65 | 2 | 1 | 1 | 1 | 1 | 2 | 1
|  |  | 2 |  | 2.75 | 19.25 | 22 | 11 |  | 55 | 2.75 | 2 | 0 | 2 | 1 | 1 | 2 | 1
|  |  | 3 |  | 2.7 | 18.9 | 21.6 | 10.8 |  | 54 | 2.7 | 3 | 0 | 0 | 1 | 1 | 2 | 1
|  |  | 4 |  | 3 | 21 | 24 | 12 |  | 60 | 3 | 3 | 0 | 2 | 1 | 2 | 2 | 1
|  |  | 5 |  | 3 | 21 | 24 | 12 |  | 60 | 3 | 4 | 7 | 0 | 1 | 2 | 2 | 1
|  |  | 6 |  | 2.85 | 19.95 | 22.8 | 11.4 |  | 57 | 2.85 | 16 | 1 | 0 | 1 | 1 | 2 | 1
[12 empty] | 30 | 9 | 5
[6 empty] | 5.9325 | 6.78 | 3.39 |  | 0.8475 | 1.9775 | 3.39
[10 empty] | 2.825 | 19.775 | 22.6 | 11.3
Note on I7: Ploen Kaewruen: 1 normal search 1 LOV