## 3. Function List
No | [9 empty] | Effort (manday) |  |  |  | Pricing by position |  |  |  | 13 | 8 | 5 | 3 | 2 | 1
|  | Task | Detial | r | sprint | Complexity | Screen | Process | Report | SM | SA | PG | Tester | SM | SA | PG | Tester 6,000 | 20 | 18 | 12 | 8 | 5 | 3
[10 empty] | 5% | 35% | 40% | 20% | 18000 | 12150 | 9700 | 7150
1 | New Car Insurance | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | New Car Insurance Activation List | 3_1_1 Show all vehicle data that received API from ddms- Select to detail for activated- Able to export raw data from list | 1 | 4 | 3 | 1 |  |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 1.2 | New Car Insurance Activation Detail | 3_1_2,3 Show detail each vehicle following selected from list screen- Click for activated- Click for deactivated (If any) | 1 | 4 | 8 | 1 | 1 |  | 1.8 | 12.6 | 14.4 | 7.2 | 32400 | 153090 | 139680 | 51480 | 0 | 36 | 0 | 0 | 0 | 0
| 1.3 | New Car Insurance Activation Report | 3_2: For download raw data from new car insurance | 1 | 4 | 5 |  |  | 1 | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 1.4 | INS Company Import - 1st year INS Sales Premium | 5_1 | 1 | 4 | 2 |  |  | 1 | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 1.5 | INS Company Export - 1st year INS Sales Daily | 5_1 | 1 | 4 | 2 |  |  | 1 | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 2.9 | New Car Insurance Edit |  | 1 | 4 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 3 | New Car Insurance search |  | 1 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Renewal | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.1 | INS Renewal - Overall Screen for Telemarketing | 4_1_1 INS Renew Call Overall, list customer that need to be followup | 1 | 1 | 8 | 1 | 1 |  | 1.8 | 12.6 | 14.4 | 7.2 | 32400 | 153090 | 139680 | 51480 | 0 | 36 | 0 | 0 | 0 | 0
| 2.2 | INS Renewal - Call Out | 4_1_2 INS Renew-Call Out, show detail for each customer | 1 | 1 | 13 | 1 |  |  | 1 | 7 | 8 | 4 | 18000 | 85050 | 77600 | 28600 | 20 | 0 | 0 | 0 | 0 | 0
| 2.3 | INS Renewal - BP claim history |  |  | 1 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 2.4 | INS Renewal - Premium quotation report | need email |  | 1 | 5 |  |  | 1 | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 2.5 | INS Renewal - Call out Results Record | 4_1_3 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.5.1 | - Case sucessful renew |  |  | 1 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 2.5.2 | - other case |  |  | 1 | 3 | 1 |  |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 2.6 | Request Edit information screen | ?? |  | 1 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 2.7 | Search Renew | ?? |  | 1 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.8 | Call plan batch |  |  | 2 | 13 |  | 1 |  | 1 | 7 | 8 | 4 | 18000 | 85050 | 77600 | 28600 | 20 | 0 | 0 | 0 | 0 | 0
| 2.9 | INS Renewal - Customer Call in | 4_1_4 Customer Call in, match telemarketing | 1 | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.10 | INS Renewal - Call in - Call out history and export |  |  | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.11 | INS Company Import /Export Screen | 5_1 | 1 | 2 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 2.12 | INS Company Import - Import Transfer Premium | 5_1 | 1 | 2 | 2 |  | 1 |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 2.13 | INS Company Import - No Claim Bonus Premium (NCB) | 5_1 | 1 | 2 | 2 |  | 1 |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 2.14 | INS Company Import - Status of issued INS policy | 5_1 | 1 | 2 | 2 |  | 1 |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 2.15 | INS Company Export - Renewal Insurance Sales Daily | 5_1 | 1 | 2 | 2 |  |  | 1 | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 2.16 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.17 | Add New Customer Profile | 4_2 Insurance Renewal Overall. | 2 | 3 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 2.18 | DLR Manual Input Customer's Information | 4_2_1 DLR Manual Input Cust Info. | 2 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 2.19 | Request Edit information download | ?? |  | 4 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 2.20 | INS Renewal - Result master | ??? |  | 4 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Management | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.1 | 1st Time Data Allocation | 6_2_1_1 1st time data allocation | 1 | 1 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.2 | Renewal STD setting - SOP Setup screen | 6_2_1_2 INS Renew SOP and PIC Setup | 1 | 2 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.3 | Renewal STD setting - Sales Team Management | 6_2_1_4 INS Renew Sales Team Mgmt | 2 | 2 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.4 | Renewal Sales Team Management | 6_2_1_5 Reallocation cust for Tele | 2 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.5 | Renewal STD setting - INS Renew Portfolio control | 6_2_1_3 INS Renew Portfolio2-7-1 Portfolio Calculate | 4 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.6 | Report - Report & Data Export of INS Renewal(to export raw data to excel file) | 6_5_2 Renew INS Data Export | 2 | 3 | 3 |  |  | 1 | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 3.7 | Report - BP Returning Report | 6_5_4 BP Returning Ratio | 2 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.8 | Report - Process & Result KPIs | 6_5_3 Process and Result KPIs | 3 | 3 | 8 | 1 |  | 1 | 1.8 | 12.6 | 14.4 | 7.2 | 32400 | 153090 | 139680 | 51480 | 0 | 36 | 0 | 0 | 0 | 0
| 3.9 | Renewal Activities Reminder | 6_2_3_1 Activities Reminder | 4 | 3 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.9.1 | - SMS |  |  | 3 | 5 |  | 1 |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 3.9.2 | - Email |  |  | 4 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 3.9.3 | - Print Letter |  |  | 4 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 3.10 | Insurance Premium Management | 6_4 INS Premium Mgmt Screen | 4 | 5 | 5 | 1 |  | 2 | 1.8 | 12.6 | 14.4 | 7.2 | 32400 | 153090 | 139680 | 51480 | 0 | 0 | 36 | 0 | 0 | 0
| 3.11 | Renewal Summary Activities Reminder Expense | 6_2_3_2 Summary SMS Expense | 5 | 5 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 3.12 | Report - Insurance Activation Function (for Manager) | 6_1_2_1 INS Activation Function (report) | 4 | 5 | 3 |  |  | 1 | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 3.13 | New Car - Insurance Portfolio Management | 6_1_2_1 INS Activation Function | 4 | 5 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.14 | New Car - Insurance Activation Management | 6_1_2_1 INS Activation Function | 4 | 5 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.15 | New Car - Insurance Portfolio Management | 6_1_1_1 For manage portfolion that will impact to call plan, 2-3 New Car INS Portfolio MGMT | 3 | 5 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 3.16 | 1st Year(Red Plate) INS report | 6_5_1 | 2 | 5 | 5 | 1 |  |  | 0.6 | 4.2 | 4.8 | 2.4 | 10800 | 51030 | 46560 | 17160 | 0 | 0 | 12 | 0 | 0 | 0
| 3.17 | Customer Management - INS Premium Mgmt Screen | 6_3_1 INS Renew Databased MGMT, 6_3_1 | 6 | 5 | 8 | 1 |  |  | 0.9 | 6.3 | 7.2 | 3.6 | 16200 | 76545 | 69840 | 25740 | 0 | 18 | 0 | 0 | 0 | 0
| 3.18 | Billing |  |  | 6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.19 | Renewal Activities Reminder Report |  |  | 5 | 3 |  |  | 1 | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 3.20 | Call in - Call out package | ??? |  | 6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.21 | Employee master - list | 6_3_2_1 Manpower and ACC Setting | 6 | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 3.22 | Employee master - Detail | 6_3_2_2 Account by Acc Mgmt | 6 | 6 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 3.23 | Customer master - list |  | 6 | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 3.24 | Customer master - Detail | 6_3_2_3 Inc Cust Ac Create | 6 | 6 | 3 | 1 |  |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Interface | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.1 | REST API received BP job data from TOPSERV |  |  | 2 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 4.2 | REST API received vehicle data from DDMS |  |  | 2 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 4.3 | REST API received customer data from TOPSERV |  |  | 2 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 4.4 | REST API receive Claim data |  |  | 2 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 4.5 | REST API Send policy data to TOPSERV |  |  | 6 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
| 4.6 | REST API - SC API - Add | New,Update,delete user, user authorize |  | 6 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 4.7 | REST API - SC API - Update |  |  | 6 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 4.8 | REST API - SC API - Delete |  |  | 6 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 4.9 | REST API - SC API - user authorization |  |  | 1 | 1 |  | 1 |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 4.10 | REST API - call result to TOUCH system |  |  | 6 | 3 |  | 1 |  | 0.4 | 2.8 | 3.2 | 1.6 | 7200 | 34020 | 31040 | 11440 | 0 | 0 | 0 | 8 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Master | [8 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 5.1 | User ( Update/ Delete) | User role assigment |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 5.2 | User Group (Update/ Delete) | Role management |  | 6 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.3 | Organization (Add/ Update/ Delete) | Organization of dealer |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 5.4 | Car Company (Toyota/Honda) |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 5.5 | Car Model (Yaris/ corolla) |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 5.6 | Province |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 5.7 | Amphur |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 5.8 | Tumbon |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 5.9 | Dealer | group dealer |  | 6 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 5.10 | Insurance |  |  | 6 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Data Migration | [8 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 6.1 | User ( Update/ Delete) | sales |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 6.2 | User Group (Update/ Delete) |  |  | 6 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.3 | Organization (Add/ Update/ Delete) | sales organize |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 6.4 | Customer Vehicel |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 6.5 | Customer |  |  | 6 | 2 | 1 |  |  | 0.25 | 1.75 | 2 | 1 | 4500 | 21262.5 | 19400 | 7150 | 0 | 0 | 0 | 0 | 5 | 0
| 6.6 | Vehicle Insurance mapping |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 6.7 | Dealer |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
| 6.8 | Insurance |  |  | 6 | 1 | 1 |  |  | 0.15 | 1.05 | 1.2 | 0.6 | 2700 | 12757.5 | 11640 | 4290 | 0 | 0 | 0 | 0 | 0 | 3
Total
[7 empty] | 52 | 19 | 11 | 38.2 | 267.4 | 305.6 | 152.8 | 687600 | 3248910 | 2964320 | 1092520
7993350
[11 empty] | 764 | 22.92
38.2
13.37
Note on I7: Ploen Kaewruen: 1 normal search 1 LOV
Note on D12: Supachai Chimpalee: No need, we can search vehicle on new car insurance activation screen
Note on D17: Supachai Chimpalee: Reduce scope, no need to implement telephone solution. Just show tel no. Ploen: This is an input screen for renewal
Note on D27: Supachai Chimpalee: Just manual call in, no need auto pop-up, no need show customer detail when received
Note on D28: Supachai Chimpalee: No automatic assign call-in to telemarketing
Note on D66: Supachai Chimpalee: Don't have billing function, please remove.
Note on D69: Supachai Chimpalee: Don't have telephone package, please reduce scope

## Sheet1
1